ClearPath Master Grant Application Readiness Checklist

Federal small-business funding | Phase I preparation and submission control

| 17 READINESS GATES Funding through submission | 16-WEEK COUNTDOWN Backward planning sequence | FINAL GO / NO-GO Controlled release decision |
| --- | --- | --- |

# Purpose

This is the working master checklist for preparing ClearPath's first federal small-business grant application. It combines the funding-path, research, product, compliance, staffing, budget, pilot, and commercialization work already documented in this folder.

Use it as a living control document. Every checked item should have supporting evidence saved in the application workspace. Requirements vary by agency and Notice of Funding Opportunity (NOFO), so the selected NOFO and agency instructions always control.

# Status And Ownership

| Application target | ______________________________ |
| --- | --- |
| Agency / institute / center | ______________________________ |
| Mechanism | ______________________________ |
| NOFO number | ______________________________ |
| Submission deadline and time zone | ______________________________ |
| Internal submission deadline | ______________________________ |
| Principal Investigator | ______________________________ |
| Authorized Organization Representative | ______________________________ |
| Application workspace owner | ______________________________ |
| Last checklist review | ______________________________ |

Priority labels used below:

•  BLOCKER - must be complete before submission.

•  STRENGTHENER - not always administratively required, but materially improves competitiveness.

•  CONDITIONAL - complete if triggered by the selected mechanism, research design, or agency.

•  DEFER - document the plan now; perform the full work after award or in Phase II.

# Gate 1: Funding Path And Opportunity Selection

☐  BLOCKER - Freeze the grant-facing product definition. Use one discipline-neutral description: ClearPath is a patient-controlled, interoffice and interdisciplinary health-information request and exchange platform.

☐  BLOCKER - Freeze the Phase I research objective. State the technical and human-factors uncertainty that Phase I will resolve, not merely the software features to be built.

☐  BLOCKER - Confirm the primary funding path. Compare NLM, NIBIB, AHRQ, NSF Seed Fund, and conditional alternatives against product fit, mechanism, budget, timeline, and eligibility.

☐  BLOCKER - Select the strongest agency, institute, or center. Record why the chosen home fits better than the alternatives and what product distortion it does or does not require.

☐  BLOCKER - Identify the exact active NOFO or solicitation. Save the official announcement, amendments, related notices, and the agency's current application guide.

☐  BLOCKER - Confirm the NOFO is open on the intended submission date. Verify opening date, expiration date, standard or special due dates, and local submission time.

☐  BLOCKER - Confirm the accepted mechanism. Determine whether ClearPath will use SBIR Phase I, STTR Phase I, Fast-Track, Direct-to-Phase-II, research grant, contract solicitation, or another path.

☐  BLOCKER - Confirm whether clinical trials are allowed, required, optional, or prohibited. Match the answer to the proposed research design.

☐  BLOCKER - Confirm participating organizations. Verify that the chosen institute or center participates in the exact NOFO and accepts applications in ClearPath's topic area.

☐  BLOCKER - Confirm award ceiling and project period. Record direct-cost limits, total-cost limits, statutory guidelines, waiver rules, and the maximum Phase I duration.

☐  BLOCKER - Confirm submission rules. Record whether the application uses ASSIST, Grants.gov Workspace, Research.gov, a contract portal, or another system.

☐  BLOCKER - Confirm resubmission, duplicate-submission, and overlapping-application rules. Prevent conflicting applications or prohibited simultaneous submissions.

☐  BLOCKER - Create a one-page opportunity decision memo. Include fit, mechanism, amount, duration, deadline, eligibility, major risks, and recommendation.

☐  STRENGTHENER - Preserve a ranked backup list. Record the next two viable opportunities and the changes each would require.

☐  STRENGTHENER - Build a compliance matrix from the NOFO. Map every instruction, attachment, page limit, and review criterion to an owner and evidence file.

# Gate 2: Program Officer And Grant Manager Engagement

☐  BLOCKER - Identify the correct program contact. Confirm the program officer, scientific contact, small-business contact, grants-management contact, and technical submission help desk.

☐  BLOCKER - Prepare a one-page Specific Aims concept summary. Include problem, gap, innovation, aims, methods, expected outcomes, company, and commercialization relevance.

☐  BLOCKER - Prepare a concise product description. Explain ClearPath without dental framing, excessive feature detail, or unsupported claims.

☐  BLOCKER - Prepare a focused question list. Cover mission fit, mechanism, Phase I scope, PI eligibility, budget, human-subjects expectations, synthetic data, and Phase II transition.

☐  BLOCKER - Contact the program officer before submission. Send the concept summary and request a short fit discussion when allowed.

☐  BLOCKER - Document the conversation. Record date, attendees, guidance, cautions, recommended mechanism, and follow-up actions.

☐  BLOCKER - Resolve PI-employment questions. Confirm whether the founder may serve as PI and the required primary-employment level during the award.

☐  BLOCKER - Resolve budget questions. Confirm founder salary, technical-lead labor, consultants, participant costs, cloud costs, legal review, security review, and indirect costs.

☐  BLOCKER - Resolve Phase I security scope. Confirm whether synthetic or de-identified data plus architecture review is acceptable and whether penetration testing can wait until Phase II.

☐  BLOCKER - Resolve research-partner expectations. Ask whether a university, health-services researcher, clinical partner, or subcontract materially improves fit or is required.

☐  CONDITIONAL - Request written clarification for ambiguous instructions. Save the response in the application record.

☐  STRENGTHENER - Ask the program officer to react to the aims, not edit the proposal. Use feedback to correct fit and scope before drafting is locked.

# Gate 3: Company Eligibility And Corporate Readiness

☐  BLOCKER - Confirm the applicant legal entity. Record legal name, state of formation, address, formation date, and good-standing status.

☐  BLOCKER - Confirm United States small-business eligibility. Verify ownership, control, place of business, employee count, and affiliate rules under the selected mechanism.

☐  BLOCKER - Confirm ownership structure. Document every owner, percentage, voting right, option, SAFE, note, and related entity.

☐  BLOCKER - Confirm no disqualifying foreign ownership or control. Complete any required foreign-risk disclosure accurately.

☐  BLOCKER - Obtain or verify the EIN. Ensure the IRS legal name and address match registration records.

☐  BLOCKER - Verify active business good standing. Resolve franchise-tax, registered-agent, assumed-name, or annual-report issues.

☐  BLOCKER - Establish a business bank account. Ensure award payments and project expenses can be segregated and reconciled.

☐  BLOCKER - Establish basic accounting controls. Use a chart of accounts capable of separating direct labor, fringe, consultants, subawards, other direct costs, and indirect costs.

☐  BLOCKER - Establish timekeeping. Create contemporaneous labor tracking for the founder, employees, and any personnel charged to the award.

☐  BLOCKER - Document founder authority. Record who may sign applications, certifications, contracts, and award documents.

☐  BLOCKER - Confirm intellectual-property ownership. Ensure the company owns or has written rights to the code, designs, documentation, domain, data model, and contractor work product.

☐  BLOCKER - Inventory open-source and third-party licenses. Flag copyleft, attribution, commercial-use, model-asset, dataset, and hosted-service restrictions.

☐  BLOCKER - Put contractor IP and confidentiality agreements in place. Do this before relying on outside-developed material in the application.

☐  STRENGTHENER - Create a capitalization table. Keep it current and consistent with registrations and investor materials.

☐  STRENGTHENER - Create a conflict-of-interest disclosure process. Capture financial interests, related parties, and organizational conflicts.

☐  CONDITIONAL - Obtain required insurance. Determine when general liability, cyber, professional liability, workers' compensation, or directors-and-officers coverage becomes necessary.

# Gate 4: Required Federal Registrations And Accounts

☐  BLOCKER - Create or verify the SAM.gov entity registration. Confirm legal name, physical address, banking information, points of contact, and representations.

☐  BLOCKER - Obtain and verify the UEI. Ensure it appears consistently in every system and application form.

☐  BLOCKER - Confirm SAM.gov registration is active through the deadline. Begin renewal early enough to survive validation delays.

☐  BLOCKER - Create or verify the Grants.gov organization account. Confirm the applicant organization is correctly linked.

☐  BLOCKER - Assign the Authorized Organization Representative. Confirm the AOR can submit and track the application.

☐  BLOCKER - Create or verify the eRA Commons organization registration. Complete this early because validation can take weeks.

☐  BLOCKER - Create or verify the PI's eRA Commons account. Use the correct PI role and link it to the applicant organization.

☐  BLOCKER - Confirm the PI's name, degree, email, and identifiers match across systems. Resolve mismatches before assembly.

☐  BLOCKER - Register in the SBA Company Registry when required. Save the registry proof document for attachment.

☐  BLOCKER - Complete any SBIR/STTR company certification. Use current ownership and affiliate information.

☐  CONDITIONAL - Create an ASSIST account and application shell. Use when the selected opportunity supports or requires ASSIST.

☐  CONDITIONAL - Create a Research.gov or SBIR.gov account. Complete agency-specific registration for NSF or another selected path.

☐  CONDITIONAL - Register subrecipient organizations. Confirm UEI, SAM, Commons, and institutional signing officials as required.

☐  BLOCKER - Store registration credentials securely. Use company-controlled access, multifactor authentication, and documented recovery methods.

☐  BLOCKER - Run a registration consistency audit. Compare legal name, address, UEI, EIN, contacts, and banking details across every portal.

# Gate 5: Research Question, Specific Aims, And Scientific Strategy

☐  BLOCKER - Define the central research question. Frame a feasibility question about consent-scoped exchange, authorization fidelity, provenance, usability, workflow burden, or interoperability.

☐  BLOCKER - Define the knowledge gap. Explain what is not known and why routine software development cannot answer it without structured research.

☐  BLOCKER - State the overall hypothesis or feasibility proposition. Make it testable within the Phase I period.

☐  BLOCKER - Limit the project to two or three coherent Specific Aims. Each aim must be measurable, feasible, and necessary to the overall conclusion.

☐  BLOCKER - Define Aim 1 deliverables and success criteria. Include required data, method, analysis, risks, and alternative approach.

☐  BLOCKER - Define Aim 2 deliverables and success criteria. Include required data, method, analysis, risks, and alternative approach.

☐  CONDITIONAL - Define Aim 3 only if it can be completed credibly. Avoid an over-scoped application.

☐  BLOCKER - Link every aim to a Phase I milestone. Align the research strategy, statement of work, timeline, and budget.

☐  BLOCKER - Define primary and secondary outcomes. Use operational definitions and measurement instruments.

☐  BLOCKER - Establish quantitative success thresholds. Examples include authorization fidelity, schema-validation rate, task-completion rate, comprehension, usability, time, and error rate.

☐  BLOCKER - Define failure criteria. State what result would show the approach is not feasible or needs redesign.

☐  BLOCKER - Define the analysis plan. Include sample size rationale, descriptive or inferential methods, missing-data handling, and decision rules.

☐  BLOCKER - Define the comparison condition or baseline. Use current record-request workflows, standard forms, or an appropriate prototype baseline.

☐  BLOCKER - Define the study population and roles. Distinguish patients, caregivers, clinicians, records staff, office staff, and technical evaluators.

☐  BLOCKER - Define recruitment and inclusion criteria. Ensure the population matches the claims and pilot use case.

☐  BLOCKER - Define data sources. Identify synthetic records, de-identified datasets, interviews, usability sessions, logs, surveys, and expert review.

☐  BLOCKER - Define the mixed-methods approach. Explain how quantitative performance data and qualitative workflow feedback will be integrated.

☐  BLOCKER - Define risks and alternative strategies for each aim. Include recruitment, comprehension, integration, schema, security, and partner risks.

☐  BLOCKER - Explain rigor and reproducibility. Address protocol consistency, version control, scripted tests, preregistered decision rules where useful, and transparent reporting.

☐  STRENGTHENER - Obtain an experienced research-methods review. Use a health-services, biomedical-informatics, human-factors, or implementation-science researcher.

☐  STRENGTHENER - Create a one-page logic model. Connect inputs, activities, outputs, short-term outcomes, and Phase II impact.

# Gate 6: Significance, Innovation, And Product Narrative

☐  BLOCKER - Quantify the problem without exaggeration. Support fragmentation, administrative burden, incomplete records, and patient-messenger claims with credible sources.

☐  BLOCKER - Define the affected users and settings. Identify the first interdisciplinary workflows rather than claiming all healthcare at once.

☐  BLOCKER - Explain why current approaches are insufficient. Compare portals, EHR exchange, HIEs, fax, release-of-information services, secure messaging, and manual patient transport.

☐  BLOCKER - Define the scientific significance. Connect authorization fidelity, provenance, comprehension, and workflow outcomes to safer information exchange.

☐  BLOCKER - Define the technical innovation. Describe the canonical ClearPath JSON model, deterministic consent scope, provenance, validation, translator contract, and auditability.

☐  BLOCKER - Define the human-centered innovation. Explain patient-readable requests, section-level choices, attribution, corrections, and revocation.

☐  BLOCKER - Separate innovation from ordinary product features. Do not present login, dashboards, uploads, or generic APIs as the research contribution.

☐  BLOCKER - Explain why the approach is interdisciplinary. Use examples spanning primary care, specialty care, hospital discharge, rehabilitation, behavioral health, pharmacy, laboratory, and imaging.

☐  BLOCKER - Remove legacy dental framing. Audit narrative, screenshots, examples, terminology, diagrams, and file names used in the submission.

☐  BLOCKER - Avoid unsupported clinical claims. ClearPath does not diagnose, prescribe, replace an EHR, guarantee HIPAA compliance, or guarantee improved outcomes.

☐  STRENGTHENER - Build a concise competitive matrix. Compare patient control, consent granularity, provenance, interoperability, small-practice accessibility, and implementation burden.

☐  STRENGTHENER - Create one consistent elevator pitch. Use it across the abstract, narrative, commercialization plan, letters, and presentation.

# Gate 7: Technical Feasibility Evidence And Prototype Readiness

☐  BLOCKER - Freeze the Phase I minimum viable research prototype. Exclude features that do not test the aims.

☐  BLOCKER - Demonstrate the provider record-request flow. Include patient selection, requested sections, purpose, recipient, expiration, and status.

☐  BLOCKER - Demonstrate the patient decision flow. Include approve all, approve selected sections, deny, request clarification, and revoke where in scope.

☐  BLOCKER - Demonstrate deterministic consent enforcement. Prove denied sections cannot enter the generated package.

☐  BLOCKER - Demonstrate ClearPath JSON generation. Use a versioned schema, validation, canonical field names, and controlled examples.

☐  BLOCKER - Demonstrate provider review. Show human-readable sections, source attribution, status, and download or acknowledgement behavior.

☐  BLOCKER - Demonstrate audit events. Cover request creation, delivery, decision, package generation, view, download, expiration, denial, and revocation.

☐  BLOCKER - Create representative synthetic patient records. Include common, sensitive, conflicting, missing, historical, and multi-source data.

☐  BLOCKER - Create negative test cases. Test malformed packages, missing consent, expired consent, wrong recipient, duplicate events, and unauthorized sections.

☐  BLOCKER - Run schema and package smoke tests. Save reproducible test results and known limitations.

☐  BLOCKER - Define provenance behavior. Every clinical item should preserve source, author or organization, timestamp, import method, and verification state when available.

☐  BLOCKER - Define correction and disagreement behavior. Distinguish patient-entered, provider-entered, imported, disputed, corrected, and superseded information.

☐  BLOCKER - Document the reviewed-import-first architecture. Direct EHR writes are not a Phase I dependency.

☐  BLOCKER - Document input and output priorities. Keep Phase I centered on ClearPath JSON, human-readable review, PDF, and CSV unless the NOFO requires more.

☐  BLOCKER - Produce an architecture diagram. Show identity, request, consent, package, translation, storage, audit, and provider-review boundaries.

☐  BLOCKER - Document technical uncertainties. Identify what must be researched rather than implying the full solution already exists.

☐  STRENGTHENER - Record a polished prototype demonstration. Use synthetic data and a scripted interdisciplinary scenario.

☐  STRENGTHENER - Create a prototype evidence appendix. Include screenshots, test summaries, schema excerpts, and workflow maps as permitted.

☐  STRENGTHENER - Establish baseline performance measurements. Record current package generation, validation, loading, and workflow timing.

☐  DEFER - Plan direct FHIR, HL7 v2, C-CDA, DICOM, NCPDP, and proprietary integrations for later phases. Do not promise unsupported production integrations in Phase I.

# Gate 8: Privacy, Security, Consent, And Regulatory Planning

☐  BLOCKER - Obtain a scoped healthcare privacy legal review. Cover HIPAA roles, authorization, state law, sensitive categories, minors, guardians, revocation, and data-sharing assumptions.

☐  BLOCKER - Determine ClearPath's likely HIPAA role in each workflow. Document whether the company may act as a business associate, subcontractor, personal health record vendor, or another role.

☐  BLOCKER - Determine whether the FTC Health Breach Notification Rule may apply. Document the conclusion and triggers.

☐  BLOCKER - Identify state-law issues relevant to the planned pilot locations. Include Texas and any partner state.

☐  BLOCKER - Identify specially protected information. Address behavioral health, substance-use records, reproductive health, HIV/STI, genetic information, and adolescent confidentiality as applicable.

☐  BLOCKER - Define consent and authorization objects. Include requester, recipient, purpose, sections, dates, expiration, revocation, and proof of patient decision.

☐  BLOCKER - Define identity and authority checks. Cover patient, proxy, caregiver, guardian, dependent, provider, and organization authority.

☐  BLOCKER - Define minimum-necessary behavior. Explain how request scope and package generation limit disclosure.

☐  BLOCKER - Define data retention and deletion assumptions. Separate research records, application records, prototype data, logs, and future production PHI.

☐  BLOCKER - Define breach and incident responsibilities at the planning level. Identify notification, escalation, evidence preservation, and partner coordination.

☐  BLOCKER - Complete a Phase I threat model. Include authentication, authorization, tenant isolation, object access, file access, secrets, logs, exports, and third-party services.

☐  BLOCKER - Complete a security architecture review. Produce prioritized remediation items and an owner for each.

☐  BLOCKER - Document encryption. Cover data in transit, data at rest, field-level encryption where used, key management, rotation, and backup protection.

☐  BLOCKER - Document access controls. Cover least privilege, role separation, provider verification, administrative access, and service accounts.

☐  BLOCKER - Document audit logging and monitoring. Identify events, retention, integrity, alerting, and access review.

☐  BLOCKER - Document secure development practices. Include code review, dependency scanning, secret scanning, environment separation, and vulnerability remediation.

☐  BLOCKER - Ensure synthetic or properly de-identified data is used before authorization to handle PHI. Verify demonstrations, screenshots, logs, and test files.

☐  BLOCKER - Prepare draft Business Associate Agreement and data-use concepts if partner conversations require them. Legal counsel should review before use.

☐  CONDITIONAL - Determine whether the software could be regulated as a medical device. Document why ClearPath is or is not providing regulated clinical decision support.

☐  DEFER - Schedule full third-party penetration testing before a real-PHI production pilot. Include budget and acceptance criteria in Phase II.

☐  DEFER - Plan SOC 2, HITRUST, or equivalent assurance based on customer requirements. Do not claim certification before completion.

# Gate 9: Human Subjects, Ethics, And Data Management

☐  BLOCKER - Determine whether each activity is human-subjects research. Separate discovery interviews, usability testing, pilot evaluation, product analytics, and clinical research.

☐  BLOCKER - Determine whether the project is exempt, non-exempt, not human-subjects research, or requires another determination. Obtain formal review when required.

☐  BLOCKER - Identify the reviewing IRB. Confirm whether the small business, research partner, or independent IRB will be responsible.

☐  BLOCKER - Draft the human-subjects section required by the mechanism. Address risk, protections, recruitment, consent, privacy, and confidentiality.

☐  BLOCKER - Define participant inclusion and exclusion criteria. Ensure they match the aims and proposed claims.

☐  BLOCKER - Address inclusion across sex/gender, race/ethnicity, age, disability, language, and digital access where required. Provide scientific justification for exclusions.

☐  BLOCKER - Create a recruitment plan. Avoid coercion and clarify relationships with pilot offices.

☐  BLOCKER - Create participant consent materials. Use readable language and distinguish research consent from health-information authorization.

☐  BLOCKER - Define participant compensation. Confirm allowability, amount, timing, and budget treatment.

☐  BLOCKER - Create a privacy-preserving data-collection plan. Collect only what is needed for the aims.

☐  BLOCKER - Create the Data Management and Sharing Plan when required. Address data types, standards, metadata, access, preservation, oversight, and limitations.

☐  BLOCKER - Define research-data security. Cover identifiers, coding, linkage files, storage, access, transfer, retention, and destruction.

☐  BLOCKER - Define adverse-event or unanticipated-problem reporting if applicable. Assign responsibility and timelines.

☐  CONDITIONAL - Complete clinical-trial forms and registration planning if the study meets the NIH clinical-trial definition. Do not guess.

☐  CONDITIONAL - Address a single IRB, reliance agreements, certificates of confidentiality, or data-use agreements. Complete when triggered.

☐  CONDITIONAL - Address vulnerable populations. Include children, decisionally impaired adults, prisoners, or economically vulnerable participants only with appropriate protections.

☐  STRENGTHENER - Conduct a health-literacy and accessibility review of participant materials. Include screen-reader, contrast, mobile, language, and cognitive-load considerations.

# Gate 10: Pilot Sites, Advisors, And Letters Of Support

☐  BLOCKER - Define the first interdisciplinary use case. Choose a workflow that is specific enough to study and broad enough to support the platform thesis.

☐  BLOCKER - Define pilot-site requirements. Include user roles, record-request volume, technology, leadership support, privacy capability, and research participation.

☐  BLOCKER - Build a partner prospect list. Include Dallas-area practices, referral relationships, rehabilitation settings, community care groups, and research partners.

☐  BLOCKER - Prepare a partner outreach packet. Include a one-page overview, research ask, time commitment, data assumptions, and expected benefit.

☐  STRENGTHENER - Secure at least one credible clinical or workflow advisor. Define role, effort, compensation, and deliverables.

☐  STRENGTHENER - Secure an interoperability or biomedical-informatics advisor. Define review responsibilities and availability.

☐  STRENGTHENER - Secure a human-factors or health-services research advisor. Ensure the research design has appropriate expertise.

☐  STRENGTHENER - Obtain letters of support from likely pilot sites. Letters should state the problem, interest, available role, resources, and nonbinding intent.

☐  STRENGTHENER - Obtain advisor commitment letters. Match the budget, biosketch, facilities, and research strategy.

☐  STRENGTHENER - Obtain customer-discovery evidence. Document interviews with patients, providers, records staff, office staff, and buyers.

☐  STRENGTHENER - Record current workflow baselines. Capture request methods, time, failure points, follow-up burden, and information gaps.

☐  STRENGTHENER - Test patient request comprehension. Identify confusing language, sensitive categories, and trust concerns.

☐  STRENGTHENER - Test provider package usefulness. Confirm which sections, sources, statuses, and formats support decision-making.

☐  CONDITIONAL - Draft subaward or consultant scopes. Align scope, budget, milestones, IP, publications, and data responsibilities.

☐  CONDITIONAL - Obtain institutional letters and signed subrecipient documents. Complete before the prime applicant's internal deadline.

# Gate 11: Team, Roles, And Staffing

☐  BLOCKER - Confirm the Principal Investigator. Document eligibility, expertise, employment commitment, and project authority.

☐  BLOCKER - Define the founder/PI role. Include project direction, grant administration, discovery, workflow design, acceptance testing, partner management, and Phase II planning.

☐  BLOCKER - Define the technical-lead role. Include architecture, implementation, security remediation, testing, documentation, and technical reporting.

☐  BLOCKER - Determine employee versus contractor treatment. Use legal and tax guidance; do not design the budget around an unsupported classification.

☐  BLOCKER - Define every key-person role and percent effort. Ensure effort is consistent across budget, justification, biosketch, and timeline.

☐  BLOCKER - Identify expertise gaps. Cover biomedical informatics, interoperability, clinical workflow, human factors, research methods, privacy, and security.

☐  BLOCKER - Prepare consultant scopes and rates. Include deliverables, hours, rate basis, travel, and letters.

☐  BLOCKER - Prepare recruitment contingencies. Explain how the project proceeds if the named technical lead or advisor is unavailable.

☐  BLOCKER - Confirm sufficient PI commitment. Reconcile the proposed $80,000 founder compensation with project months, effort, base salary, fringe, and agency rules.

☐  STRENGTHENER - Identify a grants accountant or administrator. Define pre-award and post-award responsibilities.

☐  STRENGTHENER - Create an advisory cadence. Schedule clinical, research, security, and commercialization reviews by milestone.

☐  CONDITIONAL - Prepare multiple-PI or senior/key-person leadership plans. Complete only if the structure requires them.

☐  CONDITIONAL - Prepare STTR research-institution allocations. Meet minimum small-business and research-institution work percentages.

# Gate 12: Budget, Indirect Costs, And Financial Justification

☐  BLOCKER - Rebuild the budget from the selected NOFO rules. Do not assume the working $300,000 budget is automatically allowable.

☐  BLOCKER - Confirm whether the cap is total cost or direct cost. Include fee, indirect costs, and subaward treatment correctly.

☐  BLOCKER - Confirm the project period and budget periods. Match months, effort, milestones, and cost timing.

☐  BLOCKER - Create a detailed personnel calculation. Show base salary, months, percent effort, requested salary, fringe rate, and escalation assumptions.

☐  BLOCKER - Validate founder/PI compensation. Support reasonableness with role, effort, salary basis, company policy, and agency limitations.

☐  BLOCKER - Validate technical-lead cost. Support salary or contractor rate with scope, market basis, effort, and deliverables.

☐  BLOCKER - Calculate fringe benefits consistently. Document included benefits and the rate basis.

☐  BLOCKER - Determine the indirect-cost approach. Use a negotiated rate, de minimis rate, agency-allowed default, or justified provisional method as applicable.

☐  BLOCKER - Prevent double counting. Ensure costs are not charged both directly and indirectly.

☐  BLOCKER - Price consultants and subawards. Obtain quotes, scopes, rate documentation, and required institutional budgets.

☐  BLOCKER - Price legal and privacy review. Tie the amount to Phase I deliverables rather than broad corporate legal work.

☐  BLOCKER - Price security architecture review. Distinguish it from deferred production penetration testing.

☐  BLOCKER - Price clinical, interoperability, and research advisors. Match effort and deliverables.

☐  BLOCKER - Price participant and pilot expenses. Confirm incentives, travel, site costs, and recruitment costs are allowable.

☐  BLOCKER - Price cloud and development infrastructure. Separate prototype needs from normal company overhead where required.

☐  BLOCKER - Price software, data, and model licenses. Include only items necessary for the proposed research.

☐  BLOCKER - Address equipment rules. Justify any item that meets the agency's equipment threshold and avoid unnecessary purchases.

☐  BLOCKER - Address travel. Tie each trip to a research or required grant purpose.

☐  BLOCKER - Address publication, data-sharing, and dissemination costs. Include them when required or scientifically justified.

☐  BLOCKER - Determine whether an SBIR fee or profit is allowed. Calculate and justify it under the solicitation.

☐  BLOCKER - Reconcile every number. Budget forms, justification, statement of work, consultant letters, and internal spreadsheet must match.

☐  BLOCKER - Write a detailed budget justification. Explain necessity, basis, reasonableness, and aim or milestone supported by each cost.

☐  BLOCKER - Build a cash-flow plan. Account for reimbursement timing, payroll, vendor payment, and founder transition risk.

☐  STRENGTHENER - Obtain an independent budget review. Use an experienced federal grants accountant or administrator.

☐  DEFER - Reserve Phase II costs for penetration testing, production compliance, live-PHI pilots, expanded integrations, monitoring, and commercialization scale. Show the roadmap without charging them prematurely.

# Gate 13: Commercialization And Market Evidence

☐  BLOCKER - Define the first paying customer segment. Identify the buyer, daily user, problem, trigger, and purchasing process.

☐  BLOCKER - Define the first use case and beachhead market. Avoid an undifferentiated all-healthcare market claim.

☐  BLOCKER - Estimate market size with a transparent method. Separate total addressable, serviceable available, and initial obtainable markets.

☐  BLOCKER - Define the competitive landscape. Include direct, indirect, status-quo, and build-internally alternatives.

☐  BLOCKER - Define differentiation. Emphasize patient-mediated consent, section scope, provenance, auditability, and low-integration entry.

☐  BLOCKER - Define the business model hypothesis. Compare practice subscription, usage, and network licensing.

☐  BLOCKER - Define pricing research to be performed in Phase I. Do not present untested prices as established demand.

☐  BLOCKER - Define the go-to-market sequence. Cover discovery, prototype, controlled pilot, production pilot, and conversion.

☐  BLOCKER - Define regulatory and reimbursement assumptions. State whether revenue depends on reimbursement and what procurement barriers exist.

☐  BLOCKER - Define Phase II commercialization milestones. Include production readiness, pilot conversion, integration priorities, security, and sales evidence.

☐  BLOCKER - Define the company's intellectual-property strategy. Address copyright, trade secret, potential patents, trademarks, data rights, and freedom-to-operate review.

☐  STRENGTHENER - Collect willingness-to-pilot evidence. Save interview notes, emails, and letters.

☐  STRENGTHENER - Collect willingness-to-pay evidence. Use structured interviews and avoid leading questions.

☐  STRENGTHENER - Quantify economic value. Model time saved, reduced follow-up, faster receipt, fewer incomplete requests, and avoided manual work.

☐  STRENGTHENER - Prepare a commercialization-risk register. Include adoption, integration expectations, trust, compliance cost, network effects, and sales-cycle risk.

# Gate 14: Application Components And Attachments

☐  BLOCKER - Create the final application component inventory. Use the NOFO and current agency guide, not a generic checklist alone.

☐  BLOCKER - Complete all standard forms. Verify organization, project, performance site, senior/key person, budget, and certification data.

☐  BLOCKER - Draft the Project Summary/Abstract. State problem, gap, aims, approach, expected outcome, and impact within the character or line limit.

☐  BLOCKER - Draft the Project Narrative/Public Health Relevance statement. Use plain language and the exact permitted length.

☐  BLOCKER - Draft the Specific Aims page. Ensure it can stand alone and aligns with every later section.

☐  BLOCKER - Draft the Research Strategy. Cover significance, innovation, approach, preliminary work, rigor, milestones, risks, and alternatives within page limits.

☐  BLOCKER - Draft the Commercialization Plan. Follow the mechanism-specific structure and page limit.

☐  BLOCKER - Draft the Facilities and Other Resources attachment. Describe actual resources available to the company and partners.

☐  BLOCKER - Draft the Equipment attachment. List only relevant existing or requested equipment.

☐  BLOCKER - Prepare NIH-style biosketches or agency equivalents. Use current format, contribution language, appointments, and support disclosures.

☐  BLOCKER - Prepare Other Support when required. Ensure consistency with effort, affiliations, and foreign-component disclosures.

☐  BLOCKER - Prepare the Budget Justification. Match final forms exactly.

☐  BLOCKER - Prepare the Authentication of Key Biological and/or Chemical Resources statement if applicable. Otherwise follow instructions for omission.

☐  BLOCKER - Prepare the Resource Sharing Plan if required. Address software, models, protocols, and other research outputs.

☐  BLOCKER - Prepare the Data Management and Sharing Plan if required. Align costs with the budget.

☐  BLOCKER - Prepare the Human Subjects and Clinical Trials information. Complete study records and attachments when applicable.

☐  BLOCKER - Prepare the Inclusion Enrollment Report or planned enrollment tables if required. Reconcile with recruitment targets.

☐  BLOCKER - Prepare the Bibliography and References Cited. Verify every citation and remove unsupported or irrelevant sources.

☐  BLOCKER - Prepare the Vertebrate Animals section or confirm it is not applicable. Follow the form logic exactly.

☐  BLOCKER - Prepare Select Agent Research information or confirm it is not applicable. Follow the form logic exactly.

☐  BLOCKER - Prepare consortium/subaward attachments when applicable. Include budgets, justifications, commitment letters, and institutional information.

☐  BLOCKER - Prepare consultant letters. State role, rate, commitment, and relevant expertise.

☐  BLOCKER - Prepare letters of support. Avoid generic praise; document specific resources and participation.

☐  BLOCKER - Prepare the SBA registry attachment if required. Use the current company information.

☐  BLOCKER - Prepare assignment/request forms only as permitted. Do not name prohibited reviewers or make unsupported assignments.

☐  CONDITIONAL - Prepare a Multiple PI Leadership Plan, Sharing of Model Organisms, genomic-data plan, clinical-trial dissemination plan, or other triggered attachment. Follow the selected opportunity.

☐  CONDITIONAL - Prepare a cover letter. Include only permitted information such as assignment requests, special circumstances, or required disclosures.

# Gate 15: Writing Quality, Consistency, And Review

☐  BLOCKER - Create a single terminology guide. Standardize ClearPath, patient-mediated, consent-scoped, record request, package, provenance, and reviewed import.

☐  BLOCKER - Create a claims register. For every important statistic or factual claim, record the source and where it appears.

☐  BLOCKER - Remove contradictory product descriptions. Ensure the abstract, aims, research strategy, commercialization plan, and letters describe the same project.

☐  BLOCKER - Reconcile aims, milestones, and budget. Every funded task must support an aim; every aim must have time and resources.

☐  BLOCKER - Reconcile personnel effort. Forms, budget, biosketches, support, letters, and narrative must agree.

☐  BLOCKER - Reconcile study numbers. Participant counts, sites, sessions, datasets, and analysis groups must match everywhere.

☐  BLOCKER - Reconcile timeline language. Use the same month numbering and project period across attachments.

☐  BLOCKER - Check page and character limits. Include figures, captions, tables, and attachments in the correct limit calculations.

☐  BLOCKER - Check font, margin, spacing, and file-format rules. Use current agency requirements.

☐  BLOCKER - Check every acronym. Define it on first use and avoid unnecessary jargon.

☐  BLOCKER - Check readability for nontechnical reviewers. Explain the workflow and research contribution without requiring software or healthcare-law expertise.

☐  BLOCKER - Check that the proposal is research, not a product backlog. Keep hypotheses, methods, measures, and decision rules visible.

☐  BLOCKER - Check that Phase I is feasible. Remove unsupported production promises, nationwide scope, and excessive integrations.

☐  BLOCKER - Conduct a scientific review. Use an external reviewer familiar with biomedical informatics, digital health, or health-services research.

☐  BLOCKER - Conduct a commercialization review. Use a reviewer familiar with small-business grants and healthcare purchasing.

☐  BLOCKER - Conduct a compliance review. Have privacy/security counsel or an experienced advisor review relevant claims.

☐  BLOCKER - Conduct a grants-administration review. Check forms, attachments, registrations, budget, and certifications.

☐  STRENGTHENER - Run a mock study-section review. Score significance, investigators, innovation, approach, environment, and commercialization factors.

☐  STRENGTHENER - Create a response-to-review log before finalization. Record each comment, decision, owner, and resolution.

☐  BLOCKER - Freeze content before final assembly. Establish version, date, owners, and change-control rules.

# Gate 16: File Assembly And Electronic Validation

☐  BLOCKER - Create the official application folder structure. Separate working drafts, final attachments, forms, letters, registrations, sources, and submission receipts.

☐  BLOCKER - Establish file naming conventions. Use short, stable, agency-compliant names without version confusion.

☐  BLOCKER - Convert attachments to compliant PDF files. Verify searchable text, embedded fonts, orientation, margins, and no password protection.

☐  BLOCKER - Remove comments, tracked changes, hidden text, and template instructions. Inspect every final attachment.

☐  BLOCKER - Remove sensitive metadata where appropriate. Check author names, paths, revision history, and hidden properties.

☐  BLOCKER - Upload the application early. Leave time for portal validation, correction, and AOR review.

☐  BLOCKER - Resolve every error. Do not confuse warnings with errors; document the disposition of each warning.

☐  BLOCKER - Preview the assembled application image. Review the agency-generated PDF in order, page by page.

☐  BLOCKER - Verify attachment placement. Confirm each file appears under the correct form field and no attachment is missing or duplicated.

☐  BLOCKER - Verify all links and citations. Do not rely on external links to supply required application content.

☐  BLOCKER - Verify organization and PI identifiers. Recheck UEI, Commons IDs, addresses, and contact details in the assembled package.

☐  BLOCKER - Verify totals and effort in the assembled package. Check every budget period and cumulative total.

☐  BLOCKER - Verify certifications and assurances. Ensure the authorized official understands what is being certified.

☐  BLOCKER - Obtain final PI approval. Document approval of scientific and budget content.

☐  BLOCKER - Obtain final AOR approval. Confirm authorization to submit.

# Gate 17: Submission And Post-Submission Control

☐  BLOCKER - Submit before the internal deadline. Do not plan to submit at the federal deadline.

☐  BLOCKER - Save the Grants.gov or agency tracking number. Store it with the final application package.

☐  BLOCKER - Confirm successful transmission. Save emails and portal status screens.

☐  BLOCKER - Confirm successful agency receipt. For NIH, verify the application reaches eRA Commons without unresolved errors.

☐  BLOCKER - Review the final assembled application during the viewing window. Escalate missing or corrupted content immediately.

☐  BLOCKER - Save the exact submitted package and rendered application image. Treat them as controlled records.

☐  BLOCKER - Record the submission date, time, opportunity, and version. Update the master checklist.

☐  BLOCKER - Monitor for agency requests. Assign responsibility for emails, Just-in-Time requests, and administrative questions.

☐  STRENGTHENER - Prepare for a programmatic follow-up. Keep the aims, budget, milestone, and partner facts immediately accessible.

☐  STRENGTHENER - Prepare a Just-in-Time folder. Include updated other support, certifications, human-subjects approvals, and requested documents.

☐  STRENGTHENER - Prepare for reviewer outcomes. Create paths for award, resubmission, alternate funding, and investor outreach.

☐  DEFER - Do not begin award-dependent work at financial risk without understanding pre-award cost rules. Separate ordinary company development from grant-charged activity.

# Recommended 16-Week Countdown

## Weeks 16-13: Decide And Register

☐  Select agency, mechanism, and exact NOFO.

☐  Contact the program officer with a one-page concept.

☐  Confirm PI and company eligibility.

☐  Start or validate SAM.gov, UEI, Grants.gov, eRA Commons, and SBA registrations.

☐  Freeze Phase I aims, scope, project period, and rough budget.

☐  Begin partner, advisor, and letter outreach.

## Weeks 12-9: Design The Research

☐  Finalize Specific Aims and measurable success thresholds.

☐  Finalize study design, outcomes, sample rationale, and analysis.

☐  Determine human-subjects and IRB pathway.

☐  Complete privacy, security, and regulatory scoping.

☐  Freeze prototype evidence and synthetic test scenarios.

☐  Obtain consultant and subaward scopes and cost estimates.

## Weeks 8-5: Draft The Full Application

☐  Draft Research Strategy and commercialization plan.

☐  Draft budget and justification.

☐  Draft human-subjects, data-management, facilities, and resource sections.

☐  Collect biosketches, letters, registrations, and partner documents.

☐  Run scientific, technical, compliance, and commercialization reviews.

☐  Revise against the NOFO compliance matrix.

## Weeks 4-3: Reconcile And Review

☐  Reconcile aims, budget, effort, timeline, participants, and terminology.

☐  Run mock review and resolve high-risk comments.

☐  Verify all citations, claims, page limits, and attachments.

☐  Finalize forms and agency-specific certifications.

☐  Freeze narrative content by the end of Week 3 when possible.

## Week 2: Assemble And Validate

☐  Convert and inspect final PDFs.

☐  Upload the complete application.

☐  Resolve portal errors and warnings.

☐  Review the assembled application image page by page.

☐  Obtain PI and AOR approval.

## Week 1: Submit And Confirm

☐  Submit by the internal deadline, preferably several business days early.

☐  Confirm Grants.gov and agency receipt.

☐  Review the final application during the viewing window.

☐  Archive the submitted package, receipts, and checklist.

☐  Begin monitoring and Just-in-Time preparation.

# Final Go/No-Go Review

☐  GO - Opportunity: The selected NOFO is active, eligible, mission-aligned, and financially workable.

☐  GO - Registrations: Every required registration is active and consistent.

☐  GO - Research: The application tests a real uncertainty with measurable aims and credible methods.

☐  GO - Scope: Phase I is achievable within the time, budget, team, and data available.

☐  GO - Team: The PI and key personnel are eligible, committed, and appropriately qualified.

☐  GO - Partners: Required advisors, sites, consultants, and subrecipients are documented.

☐  GO - Ethics: Human-subjects, privacy, consent, data, and regulatory pathways are correctly addressed.

☐  GO - Security: The prototype and research plan use appropriate safeguards and do not overclaim production readiness.

☐  GO - Budget: Every cost is allowable, reasonable, allocable, supported, and reconciled.

☐  GO - Commercialization: The buyer, market, differentiation, business model, and Phase II path are credible.

☐  GO - Attachments: Every required component is final, compliant, correctly placed, and within limits.

☐  GO - Validation: The complete electronic application passes portal checks and page-by-page review.

☐  GO - Authorization: The PI and AOR have approved the exact package being submitted.

☐  GO - Contingency: The team has documented award, resubmission, alternate-grant, and investor paths.

# Working Notes

Use this space for unresolved decisions, program-officer guidance, deadlines, and owners: