ClearPath Grant Application To-Do Tree

A visual dependency map for the NIH/NLM SBIR Phase I application

Working target Primary submission target: January 5, 2027. Backup target: April 5, 2027. September 5, 2026 is technically available but not the working target because company formation, registrations, advisors, writing, and review would be too compressed.

At A Glance

| Area | Status | What it means | Next dependency |
| --- | --- | --- | --- |
| Funding path | Open / mostly confirmed | NLM SBIR through PA-27-100 is the working path. | Polish one-page aims and follow up with Dr. Reddy. |
| Company setup | Locked by cash timing | A legal company is needed before federal registrations. | Choose name, use free guidance, then form Texas LLC when safe. |
| Research plan | Open now | We can keep drafting and sharpening the application before the LLC exists. | Specific Aims, Research Strategy, study protocol. |
| Prototype | Open now | App work can continue using demo/synthetic data. | Provider request, patient approval, JSON package, provenance, audit trail. |
| Submission | Locked | Cannot submit until registrations and application package are complete. | SAM/UEI, eRA, Grants.gov, SBA, final PDFs. |

Dependency Map

Read this section like a dashboard: green areas can move now, gold areas need a real-world decision or outside person, and red areas are locked until late-cycle submission work.

| 1. Funding Path Mostly open now NLM fit confirmed by Dr. Reddy PA-27-100 selected as working NOFO Specific Aims must be polished Follow-up packet should go to NLM | 2. Company + Registrations Locked behind LLC Choose legal name Form Texas LLC Get EIN SAM.gov/UEI eRA Commons, Grants.gov, SBA Registry |
| --- | --- |
| 3. Research Plan Open now One-page Specific Aims Research Strategy outline FHIR/ClearPath JSON positioning IRB/human-subjects pathway Milestones and go/no-go criteria | 4. Team + Advisors Partly locked Founder/PI decision Technical lead plan Clinical workflow advisor FHIR/informatics advisor Letters of support |
| 5. Prototype Evidence Open now Provider request workflow Patient approve/limit/deny workflow Consent-scoped JSON package Provenance/source labels Audit trail and synthetic tests | 6. Final Submission Locked until late cycle NOFO compliance matrix All attachments drafted Budget complete Portal validation Submit before January 5, 2027 |

Open Now: Work We Can Do Before Spending LLC Money

These tasks are useful immediately and do not require the company to exist yet.

| Done | Task Group | Tasks |
| --- | --- | --- |
| ☐ | Grant Strategy | Polish Specific Aims V1 into a one-page draft; Build Dr. Reddy follow-up packet; Decide whether to ask about SBIR vs STTR |
| ☐ | Application Writing | Draft Research Strategy outline; Draft Significance, Innovation, and Approach sections; Build NOFO compliance matrix |
| ☐ | Research Design | Define final research question; Set success thresholds; Draft interview guides and usability protocol |
| ☐ | Product + Prototype | Provider request workflow; Patient approve/limit/deny workflow; Consent-scoped JSON package; Provenance labels and audit trail |
| ☐ | Advisor + Partner Outreach | Create advisor target lists; Draft outreach email; Draft letter-of-support template |
| ☐ | Company Planning | Choose working legal name; Check free SBDC/SCORE/legal-clinic support; Prepare formation briefing packet |

Locked Behind Company Formation

These wait until the company legally exists. This is why October is the practical formation target for a January submission.

| Done | Task Group | Tasks |
| --- | --- | --- |
| ☐ | Legal Entity | File Texas LLC Certificate of Formation; Create operating agreement; Create company records folder |
| ☐ | IRS + Banking | Get EIN directly from IRS; Open business bank account; Keep business and personal funds separate |
| ☐ | Federal Registrations | SAM.gov and UEI; eRA Commons; Grants.gov; SBA Company Registry; Registration consistency audit |
| ☐ | Submission Authority | Identify AOR and Signing Official; Confirm PI account and role; Confirm PI employment requirement can be met at award |

Locked Behind Advisors Or Partners

These are not blocked by money as much as they are blocked by finding the right people and getting commitments.

| Done | Task Group | Tasks |
| --- | --- | --- |
| ☐ | Research Methods | Confirm study design with human-factors or research-methods advisor |
| ☐ | Clinical Workflow | Validate office/provider assumptions with clinician or operations advisor |
| ☐ | Interoperability | Review FHIR and ClearPath JSON positioning with informatics advisor |
| ☐ | Privacy + Security | Review scope with privacy/security advisor or attorney |
| ☐ | Partners | Secure letters of support; Confirm Phase I discovery support; Confirm Phase II pilot interest |

Locked Behind NLM Feedback

These become much stronger after Dr. Reddy responds to the revised one-page aims.

| Done | Task Group | Tasks |
| --- | --- | --- |
| ☐ | Aims Language | Finalize exact aims after feedback on the one-page draft |
| ☐ | FHIR Depth | Decide how much FHIR implementation belongs in Phase I |
| ☐ | Human Subjects | Clarify whether usability work creates clinical-trial or human-subjects requirements |
| ☐ | Mechanism | Confirm SBIR vs STTR if academic partner becomes important |

Month-By-Month Path To January 5, 2027

| When | Focus | Main Work |
| --- | --- | --- |
| July 2026 | Aims + outreach foundation | Finish one-page aims; build NLM packet; create advisor/partner lists; keep prototype moving. |
| August 2026 | Research design + outreach | Send follow-up if invited; start advisor and clinic outreach; draft study materials. |
| September 2026 | Company decision prep | Finalize legal name; use free SBDC/SCORE/legal-clinic guidance; build budget V2. |
| October 2026 | Company + registrations | Form LLC if financially safe; get EIN; start SAM/UEI and federal accounts. |
| November 2026 | Full application draft | Finish registrations; complete full draft; collect letters and budget support. |
| December 2026 | Final assembly | Finalize narratives, budget, forms, attachments; upload early and resolve errors. |
| January 2027 | Submit and confirm | Submit before January 5; verify Grants.gov and eRA Commons receipt; archive package. |

Critical Path

Most likely schedule blockers Company formation, SAM.gov/UEI activation, eRA Commons setup, Specific Aims finalization, advisor/partner letters, Research Strategy draft, budget justification, and portal validation.

Polish the one-page Specific Aims.

Create the NLM follow-up packet.

Make the free business-support outreach list.

Create advisor outreach drafts.

Pick 3-5 possible legal names to check.

Continue app work on provider requests, patient approval, provenance, and package generation.

Plain-English Rule

Anything that involves writing, planning, prototype work, outreach drafts, or research design can move now. Anything that requires an official applicant organization is locked until the LLC exists. Anything involving real clinical credibility is locked until advisors or partners are engaged.